## Execution Report
TEST EXECUTION REPORT — OrangeHRM Demo Manual Testing
1. Document Information
Project Name | OrangeHRM Demo Manual Testing
Document Version | 1.0
Prepared By | QA Engineer
Report Date | August 2026
Test Cycle | Cycle 1
2. Overall Execution Summary
Total Test Cases | Passed | Failed | Blocked | Not Executed
35 | 33 | 2 | 0 | 0
Pass Rate | 94.29%
3. Module-wise Execution Breakdown
Module | Total | Passed | Failed | Pass Rate
Login | 12 | 12 | 0 | 100%
User Management | 12 | 11 | 1 | 91.67%
My Info | 9 | 8 | 1 | 88.89%
Exploratory | 2 | 2 | 0 | 100%
Total | 35 | 33 | 2 | 94.29%
4. Defect Summary
Bug ID | Title | Severity | Priority | Status
BUG_001 | System accepts future birth date | Medium | High | Open
BUG_002 | System accepts unrealistic birth year | Medium | Medium | Open
BUG_003 | Shared demo environment causes inconsistent test data | Low | Low | Open
5. Conclusion & Recommendation
Of the 35 planned test cases, 33 passed and 2 failed, giving a pass rate of 94.3%. The failures relate to Date of Birth validation in the My Info module (future dates and unrealistic years) and have been logged as BUG_001 and BUG_002. A third item, BUG_003, documents a shared-environment limitation of the demo application rather than a product defect. Based on these results, the application is considered stable overall, with the Date of Birth validation logic recommended for a fix and re-test in the next cycle.
6. Sign-off
Role | Name
Tester | QA Engineer