## Test Plan
TEST PLAN — OrangeHRM Demo Manual Testing
1. Document Information
Project Name | OrangeHRM Demo Manual Testing
Document Version | 1.0
Review Date | August 2026
Testing Type | Manual Testing
Test Cycle | Cycle 1
2. Project Overview
This test plan defines the strategy, scope, objectives, resources, and schedule for manual testing of the OrangeHRM Demo web application. The purpose is to verify the functionality of selected modules, validate user inputs, identify defects, and ensure that the application behaves according to expected business requirements.
3. Objectives
• Verify the functionality of core application features.
• Validate user input fields and form validations.
• Execute positive, negative, boundary value, and exploratory test scenarios.
• Identify and document software defects.
• Produce professional QA documentation for the testing process.
4. Scope — In Scope
• Login
• Logout
• User Management
• Add User
• Edit User
• Delete User
• Search User
• My Info
4. Scope — Out of Scope
• Performance Testing
• Load Testing
• Stress Testing
• API Testing
• Mobile Testing
• Automation Testing
• Security Penetration Testing
5. Test Strategy
• Functional Testing
• Positive Testing
• Negative Testing
• Boundary Value Testing
• Validation Testing
• Exploratory Testing
Testing will be performed manually through the OrangeHRM Demo web application.
6. Test Environment
Application | OrangeHRM Demo
Browser | Google Chrome
Operating System | Ubuntu 24.04 LTS
Internet | Stable Internet Connection
Test Environment | Shared Demo Environment
7. Modules Tested
• Login
• Admin
• User Management
• My Info
8. Test Deliverables
• Test Plan
• Test Scenarios
• Test Cases
• Bug Reports
• Test Execution Report
9. Entry Criteria
• Application is accessible.
• Valid test credentials are available.
• Test environment is operational.
• Browser is properly installed.
10. Exit Criteria
• All planned test cases have been executed.
• Critical and high-priority defects have been documented.
• Test execution report has been completed.
• Test deliverables are finalized.
11. Assumptions
• Demo environment remains available throughout testing.
• Test credentials remain valid.
• No major application updates occur during the testing period.
12. Defect Management — Fields Recorded
• Bug ID
• Module
• Description
• Steps to Reproduce
• Expected Result
• Actual Result
• Severity
• Priority
• Status
13. Test Completion Criteria
• 100% of planned test cases have been executed.
• All critical findings have been documented.
• Test execution report has been prepared.
• Project documentation has been uploaded to GitHub.
14. Approval
Role | Name
Tester | QA Engineer

## Risks
10. RISKS & MITIGATION
Risk | Mitigation
Shared demo environment may be modified by other users | Re-execute affected test cases if necessary
Test data may change during testing | Use available demo data whenever possible
Internet connectivity issues | Resume testing after connection is restored